## Sheet1
| Risk | Probability(%) | Impact(1-5) | RMMM(Risk Mitigation,Monitoring and Management)
1 | Learning Django | 75 | 4 | Stay on top of in class Django activities, looked for additional tutorials and documentation and helped each other.
2 | Bootstrap implementation | 25 | 1 | Plan for back up CSS as fall back
3 | Lack of time | 87 | 5 | Prioritze most important requirements first
4 | Promising too much | 65 | 4 | Communicate with customer to determine what requirements he wants to prioritize
5 | teammates dying/sick/family emergency | 15 | 5 | Re-assign task to available team. Keep the task assignments flexible and make sure each team member is up to date.
6 | SVN struggles(loss of code) | 10 | 3 | Maintain back up code before merging and keep individual backups per developer.